## Sheet1
Sustinability Tours ToDo list
Who | When | What
STO |  | Choose a date (late May preferred) - avoid conflicts
STO |  | Arrange for Auditorium 9 a.m. to 1 p.m.
STO |  | Verify Sign-up for Pavilion from 8 a.m. to 2 p.m.
STO |  | Line up volunteers
STO |  | Confirm with Marketing: 4 spaces per tour for future residents and staff. Need names & email
STO |  | Get names & Email addresses of future residents and staff
STO |  | Signups: Arrange for Activity Desk to list all 6 tours, 8 spaces for residents per tour
Webmaster |  | Update GT website Sustainability Tour page
Webmaster |  | Add "Tour" box to GT website home page
STO & News Ed |  | May Pan News article + calendar and Activities entries
Graphic Designer |  | Set up poster & print one copy
STO |  | Coodinate with Bri about videos
STO |  | Send notice to Kya about Sustainability Tours
Distrib |  | Post posters on bulletin boards (2 weeks before signup)
Display stand |  | Update display stand if necessary
STO & Grounds |  | Arrange for cleaning of recycle center befor tour
Grounds |  | Make sure there are no mowers & blowers (In 2023rChalet mower was noisy)
Grounds |  | Get cone for first EV charging station postion (for tour participants to stand)
STO & Recyc. |  | Provide tri-fold brochures (Green Team and Recycling)
STO |  | Contact volunteers about walkthroughs
STO & Vol |  | Lead walk-through #1
STO & Vol |  | Lead walk-through #2 if necessary
STO | Tour-3 days | From Marketing: Get list of future residents and staff attending, with times and email addresses
STO | Tour-3 days | Send email reminder to all attendees (residents and future residents)
STO | Tour-2 days | Post notice on Kya if all trips are not filled.
STO | Tour day | Get lists of resident signups from Activity Desk
EV Expert | Tour day | Bring an EV to charging station
STO | Tour day | Bring tri-fold brochures, display stand, blank name tags
STO | Tour day | Bring ice bucket with ice and reusable glasses. Use water from sink.
STO or Greeter | Tour day | Check participants in. Give future residents name tags.
Greeters | Tour day | Talk to participants about Green Team
Leaders | Tour day | Lead tours (groups of up to 12)
Experts | Tour day | Talk to participants about their topic
Webmaster | Tour+1 day | Update website to reflect that tour has taken place.
STO | Tour+3 days | Send rreport to GT SC and thank you to Marketing
STO=Sustainability Tours Organizer (Evie)
Webmaster (Evie)
News Ed = GT News Editor (Jean)
Graphic Designer (Evie)
Distrib - Poster distributor (MJ & Evie)
Display Stand (Evie)
Grounds (Adam or Melissa)
Recyc = Recycling organizer (Peggy J.)
Vol=Volunteers (Leaders, Experts and Greeters)
<><><>
Kya announcement: (submit two weeks before tours)
Message title: Sustainability Walking Tours
Event Date: [fill in date]
Event Location: Starts and ends at Pavilion
Event Times: Tours start every half hour from 9 to 11:30 a.m.
Details: The Green Team invites you to take a guided tour around the Panorama campus to learn what has been
done and what is planned for moving in the direction of sustainability - from planting trees to adding solar panels,
EV charging stations and native plants. Walking distance is about .75 miles and time is around 1.5 hours. See
https://panoramagreenteam.org/events |  |  | for details including a map of the tour route.
Dates to be shown on Kya: {2 weeks before tour through tour date]
Submitted by: Evie Starr, Green Team
Phone: 5990
<><><>
Message to Activity Desk to be submitted by deadline on month before tour:
Here are the Green Team Calendar and Activities entries for the
May 20xx Panorama News
Entry for May 20xx Calendar:
[Date]: 9a Sustainability Tours PAV
Note to Activity Desk: There will be tours starting at 9, 9:30, 10, 10:30, 11 and 11:30 a.m. in the Pavilion but I wasn't sure how to list them here. The description under Activities explains the times. The last tour will end around 1 p.m.
Entry for May 20xx Activities & Events:
[day of week, date]: Sustainability Tours: 9, 9:30, 10, 10:30, 11 and 11:30 - The Green Team will conduct walking tours showcasing sustainable aspects of the campus
including solar panels, EV charging stations, and much more. Walking distance will be about .75 miles, and each tour will take about 1.5 hours.
Sign up at the Activity Desk. Learn more at
panoramagreenteam.org/events/
Thanks,
Evie Starr, phone 5990